## Master Project Tracker
Task ID | Module / Phase | Task Name | Assigned To | Status | Priority | Start Date | Due Date | Notes / Blockers
TSK-001 | 00 - Project Management | Draft Project Charter | Student | Completed | High | 2026-07-01 | 2026-07-05 | Approved by supervisor
TSK-002 | 01 - Research | Literature Search & Synthesis | Student | In Progress | High | 2026-07-06 | 2026-08-01 | 10 papers added to Matrix
TSK-003 | 05 - Design | System Architecture Design | Student | Not Started | Medium | 2026-08-02 | 2026-08-15 | Pending lit review completion